MANAGEMENT AND DEVELOPMENT OF THE MILLENNIUM WOOD FOR PEOPLE AND WILDLIFE

Reference Millennium Wood Management Plan

Nottinghamshire Wildlife Trust Document (Farnsfield Hadleigh Park)

# Site is 3.97 Ha

# Subdivide this into 5 sections of 0.794 Ha on average

Contractor would deal with one section each year, and path maintenance as the site progresses.

# Identify the 30% of each section to be left alone

# Remaining 0.556Ha (70%) to be thinned by 25% to reduce canopy

# Thinning

When thinning is carried out it will be light (less than 25% canopy removal) and often, for example on a 5year cycle. Works will take place within 70% of the compartment, leaving the other 30% as a buffer.

# Aim for more aggressive thinning near broad paths to create 2-zone rides

# Remove non-native invasive shrubs (less than 10 in total identified)

As the thinning takes place light will reach the woodland floor and increase the understory. This will be supplemented with the planting of shrubs, woodland flowers and shade-bearing tree species. Some of the cherry have suckered along the edges of the footpath, and most of these will be removed over the period, though circa 30% will be left to create pinch points on the footpath edge, and to break up the straight line of the path.

Deadwood where practical and safe to do so will be left or created on site, some will be collected up into piles while other deadwood will be left standing. Excess brash may be used for dry hedging where appropriate. Ring barking of trees to increase this to circa 1m3 per Ha.

# Two zone paths/rides

Paths need to be 2 meters wide, with buffer zones to be decided according to the path location. For example, the path running along the south side should have buffer zones on both sides whereas the path on the east side already has a hedge, so would only need a buffer on its west side.

Paths would need to be cleared annually, and the buffer zones trimmed every four years. This would create different layers of vegetation in different parts of the site encouraging biodiversity. Buffer areas may be planted by volunteers as the site develops

# Hedge Laying Southwest borders

# To be completed over the course of 5 years, costed separately with contractor

| YEAR | WOODS | PATHS | VOLUNTEER PLANTING |
| --- | --- | --- | --- |
| 2018 | Thinning zone 1 | Zone 1 | Bulbs zone 1 |
| 2019 | Thinning zone 2 | Zone 2 | Plugs zone 1 Bulbs zone 2 |
| 2020 | Thinning zone 3 | Zone 3 | Plugs zone 2 Bulbs zone 3 |
| 2021 | Thinning zone 4 | Zone 4 | Plugs zone 3 Bulbs zone 4 |
| 2022 | Thinning zone 5 | Zone 5 | Plugs zone 4 Bulbs zone 5 |

# Lesley Healy

March 2018